## Sheet1
Phase | Task | Hours | Hourly Rate ($) | Cost ($)
Planing |  | 159 |  | 1984
| Create meeting agenda for our first meeting. | 3 | 5 | 15
| Set meeting date and time and send email with it | 1 | 1 | 1
| Create Stakeholders Grid. | 4 | 7 | 28
| Create Stakeholders Analysis. | 16 | 10 | 160
| Create Communication management plan. | 8 | 15 | 120
| Create Team Charter. | 24 | 20 | 480
| Create work breakdown structure. | 30 | 15 | 450
| Create risk management plan. | 25 | 10 | 250
| Create time estimation for project. | 24 | 10 | 240
| Create schedule for project. | 24 | 10 | 240
Designing |  | 208 |  | 5200
| Create UI & UX for app. | 72 | 25 | 1800
| Review App UI & UX. | 10 | 25 | 250
| Design Admin panel. | 48 | 25 | 1200
| Design Vendors panel. | 48 | 25 | 1200
| Design App tools (emails & notifications). | 15 | 25 | 375
| Design App help area. | 15 | 25 | 375
0
Implementation |  | 1584 |  | 45360
| Develop user app. | 720 | 30 | 21600
| Develop Admin Panel. | 240 | 30 | 7200
| Develop Vendors Panel | 240 | 30 | 7200
| Develop Help area. | 120 | 30 | 3600
| Add main security tools | 72 | 30 | 2160
| Connect all API. | 72 | 30 | 2160
| Connect any third-party app. | 48 | 30 | 1440
| Finish security process. | 72 | 30 | 2160
Monitoring & Testing |  | 157 |  | 2251
| Test user app. | 24 | 15 | 360
| Test Admin Panel. | 10 | 15 | 150
| Test Vendors Panel. | 10 | 15 | 150
| Review App's code. | 48 | 15 | 720
| Check security standards. | 10 | 15 | 150
| Test API. | 48 | 15 | 720
| Make a test Purchase. | 1 | 1 | 1
| Check Third-party apps. | 5 | 15 | 75
| Check Server speed. | 1 | 1 | 1
Deploy |  | 288 |  | 7620
| Take approves. | 20 | 20 | 400
| Update app after testing | 100 | 30 | 3000
| Upload codes to server. | 48 | 30 | 1440
| Launch App V1.0 | 48 | 30 | 1440
| Start app updating plan. | 72 | 15 | 1080
0
Finishing |  | 52 |  | 260
| Make a final meeting with team. | 4 | 5 | 20
| Collect reviews. | 4 | 5 | 20
| Make a final meeting with main client. | 4 | 5 | 20
| Take client review. | 16 | 5 | 80
| Team appraisal | 24 | 5 | 120
|  |  | Tools Tools Cost | 62675
Tools |  | Description | Cost ($)/Month | Note
| Dedicated Server (Hosting) | Processors:1 CPU Cores:16 CPU Threads:16 Base Freq:2.1 1TB HDD & 32GB RAM | 146
| SSL Certification | Free SSL | 0
| Domain name | .com domain | 1
| App store license | App Store | 8.25
| Google play License | Google Play | 25 | One time payment
| Microsoft store License | Microsoft Store | 99 | One time payment
| Cloudflare License | Pro Plan | 20
| Video Streaming | Video | $0.01/GB (min 9 $/m) | Based on using
| Tickiting System | Tickiting | 99
| Chat Plugin | Chat | 50
| Marketing analysis Plugin | Marketing Analysis | 29
| Payment Gateway Fees | Payment Gateway | 99
|  |  | Tools Tools Cost | 461.25
|  |  | One time Costs | 124
|  |  | Total Project Costs ($) | 63260.25
|  |  | Total Monthly Costs ($) | 461.25
Assumptions
We used Free SSL based on tech. team recommendations, other types may cost
More app users will cause server upgrading
All team must have 3-years experience at least
Tools and plugin fees may change depending on provider