## Sheet1
Risk Management
Risk Name | Description | Probabilty | Impact | Stratigy | Solution
Bank's non-approval of financing | In case of the financier or bank refuses to finance the project, or if the bank's position changes after the original consent to finance the project, | Moderate | Failure | Avoid | Making secondary contracts and agreements with banks and other institutions for emergency financing in case of any problems with the main financier.
Country laws changed | In case of changing some laws or issuing a new law that conflicts with the project policy | Rare | Extreme | Mitigate | An attempt will be made to address this problem as much as possible, while informing the legal department of the company of this possibility in order to take into account the appropriate solution, while adhering to the legal part regarding the non-application of this law retroactively.
Seeing a competitor during implementation | Launching a competitor for the same service or a service that is very similar to the basic idea of ​​the application | Likely | Extreme | Mitigate | Basically, cooperation will be made with the legal side to create a patent or innovation for the idea of the project, but in the event that this does not happen for one reason or another, an attempt will be made to make cooperation contracts with the competitor or to speak with the financier to make a financial offer to acquire the competitor.
Project idea leaked | In case of the project idea is leaked before the launch to a potential competitor | Rare | Moderate | Avoid | Care will be taken to establish a patent before starting the implementation of the project to the extent sufficient to avoid this problem
The occurrence of legal problems during implementation | In case of a legal problem related to the project or part of it during implementation. | Rare | Extreme | Transfer | The legal department will be involved in the necessary work to solve these problems, and in the event that it is impossible to solve this problem, a final solution will be resorted to, which is to transfer the company to another country.
A health pandemic | In case of a health pandemic affecting the continuation of the normal workflow | Rare | Moderate | Mitigate | Work will be continued normally with other solutions such as reducing working hours with canceling weekly vacations to compensate for losses, and the possibility of working remotely or from home, with continuous follow-up in the event of the absence or apology of one of the team members, while taking quick solutions in that case, either by hiring a new employee or using a source external or freelance.
A change in the company's board of directors and policy | In case of a change to a member of the Board of Directors or a complete change of the Board of Directors during the implementation of the project, which resulted in a change in the company's policy, which could affect the project | Rare | Moderate | Avoid | Putting this point in the contracts, while making sure to put a penalty clause that prevents any change in plans without convincing reasons
The occurrence of a workplace emergency scenario | In case of any emergency in the workplace, such as a fire, gas leak, or even a natural disaster | Rare | Moderate | Mitigate | Emphasis is placed on the means of protection available in the workplace, along with simulating the situation with appropriate training to deal with these circumstances. In case that the place is damaged in a way that impedes work, work will continue from home until these problems are resolved or untill the place is changed.
Design does not meet customer expectations | In case that the design does not meet the customer's expectations. | Moderate | Extreme | Avoid | Before starting the design phase, it will be confirmed with the client on the basic points of the design such as the colors, fonts and shapes used and the division of the application, as well as making sure to display more than one design that already exists for competitors or similar applications. Also, care is taken to keep the customer constantly informed of every part that is implemented within the basic design
Programming does not match the proposed design | In case that the coding does not match the current design. | Rare | Extreme | Mitigate | Coding will be continuously monitored daily by one of the team members to ensure that its conforms to the proposed design.
Server hacked | If the application is hacked in one way or another, or a security problem occurs that threatens the applicatio. | Moderate | Failure | Avoid | A backup copy will be made and uploaded to another server to be published quickly in the event that this case occurs. Also, it will be ensured that the necessary security precautions are put in place to fully secure the application.
Visits to the application continue to rise. | In case of a sudden increase in the number of visits to the application, which may lead to a stoppage of server services or a slowdown in the server response. | Likely | Extreme | Avoid | Confirm subscribing with a service provider who allows the possibility of changing the server capabilities (upgrading) immediately without downtime and affecting the mechanism of the application, with continuous follow-up of the number of visits and making statistics periodically.
A critical error occurred in the application | In case of a sudden error which lead to a stoppage of app. | Likely | Failure | Mitigate | A backup copy will be made and uploaded to another server to be published quickly in the event that this case occurs. Also, it will be ensured that the necessary investigation happen to avoid this error again.
A problem has occurred in one of the third-party apps. | In case of happening a problem to one of the third-party apps which may affect the app functionality. | Moderate | Extreme | Mitigate | A quick action will be to hold this app and investigate the error and contact the developer of this app to take a quick action or permanently terminate this app.
A problem has occurred in payment gateway. | In case of happening a problem to payment gateway which may affect the app functionality. | Moderate | Extreme | Avoid | Be sure to connect a well-known payment gateway provider with 24h/7d customer service, while also providing more than one payment gateway within the application.