## Project tasks
Project name | Get started with Project
Project manager | Ahmed Hossam
Project start date | 2023-05-08 09:00
Project finish date | 2023-05-30 17:00
Duration | 22 days
% complete | 0%
Exported on | 2023-05-08 01:25
Task number | Outline number | Name | Assigned to | Duration | Depends on | Start | Finish | % complete | Bucket | Dependents (after) | Effort | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items | Labels | Priority | Sprint
1 | 1 | Task A |  | 3 days |  | 2023-05-01 09:00 | 2023-05-03 17:00 | 0% | Bucket 1 | 2FS, 3FS |  |  |  | No |  |  |  |  | Medium | Backlog
2 | 2 | Task B |  | 4 days | 1FS | 2023-05-09 09:00 | 2023-05-12 17:00 | 0% | Bucket 1 | 4FS |  |  |  | No |  |  |  |  | Medium | Backlog
3 | 3 | Task C |  | 2 days | 1FS | 2023-05-11 09:00 | 2023-05-12 17:00 | 0% | Bucket 1 | 5FS, 6FS |  |  |  | No |  |  |  |  | Medium | Backlog
4 | 4 | Task D |  | 5 days | 2FS | 2023-05-15 09:00 | 2023-05-19 17:00 | 0% | Bucket 1 | 7FS |  |  |  | No |  |  |  |  | Medium | Backlog
5 | 5 | Task E |  | 1 day | 3FS | 2023-05-15 08:00 | 2023-05-15 17:00 | 0% | Bucket 1 | 7FS |  |  |  | No |  |  |  |  | Medium | Backlog
6 | 6 | Task F |  | 2 days | 3FS | 2023-05-15 09:00 | 2023-05-16 17:00 | 0% | Bucket 1 | 8FS |  |  |  | No |  |  |  |  | Medium | Backlog
7 | 7 | Task G |  | 4 days | 4FS, 5FS | 2023-05-22 09:00 | 2023-05-25 17:00 | 0% | Bucket 1 | 8FS |  |  |  | No |  |  |  |  | Medium | Backlog
8 | 8 | Task H |  | 3 days | 7FS, 6FS | 2023-05-26 09:00 | 2023-05-30 17:00 | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium | Backlog